## Header
Three Point Estimate
Instructions:
| Project Code/Name: | SSG002 Student Marketing Services Infrastructure Migration Student Marketing Services Infrastructure Migration
| Project Manager | Maurice Franceschi
| Estimate Date | 2012-10-10
| Project Stage | Planning
| Estimate Reference | Planning-01
Notes and Assumptions
Please record any notes and assumptions on which the estimate is based.
Estmate Contributors
| Role |  | Name | Signature
Include all contributors here. Remember to include key IS and business stakeholders such as Unix FM, Architecture, Finance and Procurement where appropriate. Without this information the estimate cannot be approved!
Neil Grant
Mike McMonagle
John Chan
Chris Cord
Sue Woodger
Maurice Franceschi
Enter the a,m, and b values for each Task into columns C,D and E. The E and SD values for each task will be calculated and displayed in columns F and G. A task estimate with at least 95% confidence and the required task booking value is calculated and displayed in columns H and J. Based on the individual task estimates the E value and SD for the project will be calculated and displayed as will the overall work estimate for the project with at least 95% confidence levels.

## Three Point Estimates
Methodology Stage or Activity | Task | Team(s), Role(s) or Individual(s) Responsible for Execution of Task | Best Case Estimate a | Most Likely Estimate m | Worst Case Estimate b | E Value | SD Value | Task Estimate 95% Confidence | SD**2
| Project Management | Maurice | 8 | 11 | 14 | 11 | 1 | 13 | 1
| Quality Assurance | Ailsa, Steven | 2 | 3 | 4 | 3 | 0.4 | 3.8 | 0.2
| Infrastructure Support | Neil, Apollon | 2 | 3 | 4 | 3 | 0.4 | 3.8 | 0.2
| Training | not applicable | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initiation | Initiation | Maurice | 1 | 1.5 | 2 | 1.5 | 0.2 | 1.9 | 0.1
Planning | Planning | Maurice | 2 | 3 | 4 | 3 | 0.4 | 3.8 | 0.2
Business Analysis | Business Analysis - IS Apps needs for I/F | Sue | 1 | 2 | 3 | 2 | 0.4 | 2.8 | 0.2
| Business Analysis - Functionality, Admin Needs | Sue | 2 | 3 | 4 | 3 | 0.4 | 3.8
| Business Analysis - Integrations with other Systems | Sue | 2 | 3 | 4 | 3 | 0.4 | 3.8
Systems Design | Systems Design - File Systems Access | Neil, Mike | 1 | 1.5 | 2 | 1.5 | 0.2 | 1.9
| Systems Design - Integrations with Other Systems | Neil, Mike | 1 | 1.5 | 2 | 1.5 | 0.2 | 1.9 | 0.1
| SDS | Mike | 2 | 3 | 4 | 3 | 0.4 | 3.8
| TAD | Neil | 2 | 3 | 4 | 3 | 0.4 | 3.8
Build | Dev Test Live Environments | Neil | 15 | 18 | 21 | 18 | 1 | 20 | 1
of four | Build - Rewrite Deprecated Code | Mike | 8 | 12 | 16 | 12 | 1.4 | 14.8 | 2
Applications | Peer Testing - Check Migration of Code | Other Dev Team | 4 | 6 | 8 | 6 | 0.7 | 7.4 | 0.5
| System Documentation - SDD (new) | Mike | 2 | 3 | 4 | 3 | 0.4 | 3.8 | 0.2
| Implementation Plan | Mike | 0.5 | 1 | 1.5 | 1 | 0.2 | 1.4 | 0.1
Integration | Integration testing | Neil | 5 | 6 | 7 | 6 | 0.4 | 6.8 | 0.2
Acceptance | Acceptance Testing | Ailsa, Steven | 3 | 4 | 5 | 4 | 0.4 | 4.8 | 0.2
Deployment | Deployment | Neil | 4 | 6 | 8 | 6 | 0.7 | 7.4 | 0.5
Closure | Closure | Maurice | 1 | 2 | 3 | 2 | 0.4 | 2.8 | 0.2
0
| Totals |  |  |  |  | 97 |  | 118
| E (Project Work) |  | 97
| SD (Project Work) |  | 3
| Project Estimate > 95% Confidence |  | 118

## Estimate By Team (IS Apps)
IS Apps Section | Team | Estimate (Days) | SD**2
Project Services | Project Services |  | #REF!
Development Services | Development Team
| Configuration Team |  | #REF!
| Development Technology |  | #REF!
Production Management | Applications Management
| Technology Management |  | #REF!
Service Management | Delivery and Integration
| Multimedia |  | #REF!
Directors Office | Directors Office
| Total Days | 0